## Slide 1: Military Construction in the Arctic Lessons Learned and Future Challenges
1
Julie Mages, P.E.
611th Civil Engineer Squadron
Notes: 1

## Slide 2: Overview
Our AOR
Alaska Radar Sites (ARS) & Eareckson Air Station (EAS)
Cape Lisburne and the Seawall Repair

## Slide 4: Area of Responsibility

## Slide 5: Area Cost Factors UFC 3-701-01
Location | Area Cost Factor
Cold Bay LRRS | 4.55
Eareckson AS | 4.55
Most ARS | 2.51-2.53
Murphy Dome | 2.25
* Cost adjustment factor to change from a common location cost to location-specific costs

## Slide 6: Eareckson Air Station

## Slide 7
Key Mission Partners
  21 Space Wing: Space object tracking and intel for AFSPC, USNORTHCOM, AF ISR
  Missile Defense Agency: Long-haul, interceptor comm for USNORTHCOM and missile tracking
  10,000 ft runway
    Only emergency/weather divert airfield in 1,400 mile radius -- Air Bridge for Travel to/from Asia-Pacific
  Weather Challenges/Increased Costs
    Fuel Barge Delays, Flights to/from Cancelled...
    Aging Infrastructure
Eareckson Air Station (Shemya)
Critical Support for Ballistic Missile Defense Capability - Homeland Defense!

## Slide 8: Weather and Logistics
Fuel barges to Eareckson usually have to wait 2-6 months to make delivery
  Fuel Pier exposed to weather/strict offloading requirements
Creative Solutions for offloading heavy equipment
  Beach Landing at a WWII ordinance disposal site
  USAF/ADEC and UXO Technician

## Slide 9
15 Long-Range Radar Sites
O&M via 10yr BOS Contract (ARCTEC)
Federal Aviation Agency Cost-Shares 12 Sites
Harsh Weather/Environment Create Unique Infrastructure and Logistical Challenges
Alaska Radar System (ARS)
Tin City
Fort Yukon
Cape Lisburne
Barter Island
Provide 24/7/365 Air Picture for Warning, Assessment, Command and Control Ensuring
Air Sovereignty of U.S. and Canada
Intercept by two USAF F-22s & two RCAF CF-18s, 20 Apr 17
169 Air Defense Sq
(Alaska ANG)
Barter Island
Notes: FAA Cost-Share Does Not Include Barter Island, Oliktok, and Cape Lisburne

## Slide 10
Cape Newenham LRRS

## Slide 11: Road to Top Camp
Tin City Piston Bulley
Tin City Road Work

## Slide 12: ARS by the Numbers
$4 Billion in Facilities, Equipment and Materiel
29,000 ft of Runways/4 Million ft2 of maintained primary runway surface
59 miles of roads
44 Prime Power/Emergency Generators
Diesel and MOGAS Capacities > 1.8M gal
FPS-117 Long Range Radar/FAA Equipment & Radios
Indian Mountain LRRS

## Slide 13: Challenges/Lessons Learned at the ARS Sites
Environmental Considerations
Weather and Logistics
Security

## Slide 14: Environmental Conditions
Land Use Control Management
  Land use controls are supplementary to engineering controls for short-term and long-term management to prevent or limit human and environmental exposure to hazardous substances, pollutants, or contaminants.
Environmental Restoration
Marine Mammals
Endangered Animals
Cultural Resources
Tribal Relations
Migratory Birds

## Slide 15: ARS Logistics
Transportation – primarily airlift
  Airfield sites, Ft Yukon supported by military, and contract air
  Indian Mountain, Sparrevohn can only be supported by air
  Village sites supported via commercial air
Other Modes
  Murphy Dome, Oliktok supported via road system
  Coastal sites, Tatalina, Ft Yukon supported by sealift and river barge
Influences
  Major influence is weather
  Few commercial carriers; expensive
Annual Resupply for Fuel
  Village sites purchase fuel locally

## Slide 16: Security
All people going to/from any site need background checks
Facilities have different levels of security
Must have a reason to be on site

## Slide 17: Cape Lisburne, LRRS

## Slide 18: Cape Lisburne
  706 miles NW of JBER
  Within the Alaska Maritime National Wildlife Refuge
  Nearest community:
    Point Hope, 25mi
Cape Lisburne LRRS

## Slide 19: Airfield & Seawall
Airfield
  Built 1952
  One gravel surface runway
  4,100 ft X 150 ft
  Only means of accessing the site in the winter months
  Relocation not feasible
Seawall
  Essential to the airfield runway
  Natural slope armored with boulder rip-rap
  Protected by near shore sea ice in fall/winter/spring
Seawall

## Slide 21: Timeline of Events
Shorter winters and less sea ice accelerating coastal erosion
Major storm September 2012
Exhausted existing quarry
New storm November 2013
June 2014 USACE surveys/studies
Construction Awarded to Orion Marine Construction Sep 2015, $41M
September 2012 – waves on runway
November 2013 – hole in seawall
Summer 2014 – ARCTEC repairs seawall
Summer 2014 – ARCTEC repairs seawall
Notes: Discuss alternatives
- Dolos, sheet piles, relocation of runway, spot repair
Runway critical to mission

## Slide 23: Construction Challenges
Materials/Fuel Delivery
Quarry/Explosives Requirements
Construction Season
Mancamp/Sewage Treatment
Wildlife

## Slide 24
Barging and Logistics
Beach Landings

## Slide 25
Quarry Operations
Notes: Quarry operations require significant quantities of explosive materials, which are stored on Air Force property under an approved waiver while a final DDESB storage plan is developed. The storage location meets Q-D requirements from the radar and bottom camp, but hazards utility lines that support the radar. The location cannot be changed and the utilities cannot be buried without impacting wetlands or creating further hazards. The contractor has encountered challenges blasting difficult rock and has requested increased storage.

## Slide 28: Construction Seasons
Notes: -Sea Ice -Daylight

## Slide 29: Limited Beds/Kitchen Space
- Sewage Treatment (Life Water Engineering) - Entertainment - Food: Preservation/Preparation/Serving - Bear Proof
- 16 available beds in main facility - Other people need to use the site

## Slide 30
Fuel and Explosives
- Critical to project schedule
Fuel: $4.92/gal, need +320,000 gal per construction season, temporary storage, delivery schedule

## Slide 32
Food Control/Management
General Awareness
Bear Interaction Management Plan
No Harassment Policy

## Slide 33
Walrus Monitoring

## Slide 34
TIME and $$$

## Slide 35
BUT AREN’T THEY CUTE?

## Slide 36
Seawall: Before and After
Construction Challenges
Notes: Wave Action/Storms
Rock and Equipment
Redundancy
Air Traffic and Schedule

## Slide 37: Conclusion
Expensive
Understand your problem
Know your location
Changing Climate
Environmental Preservation
Success comes from detailed logistics and planning

## Slide 38: Questions?